rooted/pwr

Project Management + Strategic Implementation Fellowship

Cohort Learning Scope and Sequence

2026 Pilot Fellowship

Anchor Appreciative Inquiry Question What becomes possible when grassroots stakeholders skill-build sustainable and scalable project management practices for social innovations that impact multi-generational futures?

# Program Overview

Design premise: project management as power-sharing infrastructure for social innovation.

| Program Window | July – November 2026, with intensive skill-building in July and August, an in-person Baltimore convening in September, and applied practice plus capstone reflection in October and November. |
| --- | --- |
| Participant Model | Three-person organizational team: community steward representative, project lead, and resident/community stakeholder. |
| Session Rhythm | Tuesday and Thursday cadence only. Primary learning sessions are 2-hour virtual sessions; one in-person convening is scheduled for mid-September; assignments and office hours occur between sessions. |
| Design Thread | Culturally responsive project management, Strategic Doing integration, catalytic capital readiness, collaborative table management, stakeholder alignment, scalable execution, and sustainable measurement. |
| Monthly Commitment | Approximately 20 hours per month, including readings, assignments, and live virtual sessions. |

# Program Architecture

| Phase | Timeframe | Essential Question | Focus | Core Outputs |
| --- | --- | --- | --- | --- |
| Pre-Launch | April–June | What foundations must be in place before a team can benefit from an applied fellowship? | Readiness, application, diagnostics, live-case selection | Readiness intake, baseline diagnostic, draft initiative profile |
| Phase 1 | July | What does culturally responsive project management require in grassroots social innovation? | Shared language, power, roles, and strategic clarity | Initiative Profile, Role + Decision Map, Strategy Clarity Brief |
| Phase 2 | August | What disciplined practices move a community-rooted project from intention to coordinated action? | Scope, sequencing, collaborative tables, and communication rhythms | Scope + Outcomes Sheet, 90-Day Work Plan, Table Design Memo, Share-Out Template |
| Phase 3 | September | How do teams practice implementation in place, in real time, and under public conditions? | Baltimore convening, scenario practice, and peer consultancy | Risk + Scenario Plan, Fall Action Commitments, revised implementation plan |
| Phase 4 | Oct–Nov | What helps teams sustain execution, generate proof points, and internalize new practice? | Adaptation, measurement, sustainability, and capstone reflection | Progress Tracker, Sustainability Plan, Capstone Deck, Proof Points Memo |

# Detailed Scope and Sequence

Including pre-work, between-session assignments, and post-session deliverables.

Pre-Launch ¦ April–June 2026 What foundations must be in place before a team can benefit from an applied fellowship?

Purpose: ensure each team enters the fellowship with a live case, a complete team, and a baseline understanding of current implementation strengths and gaps.

| Date / Time | Session | Learning Objectives | Agenda / Methods | Pre-work | Output(s) |
| --- | --- | --- | --- | --- | --- |
| April 1–May 8 Application Window | Application | Surface organizations with a live initiative, tested commitment, and readiness for team-based participation. | Call launch, information webinar, and application package asking each applicant to name a live case, implementation barriers, and desired proof points. | Applicants prepare concept paper and identify their three-person team. | Concept paper submission; proposed live case. |
| May 11–June 5 Review + Finalist Conversations | Review + Finalist Convs. | Assess strategic alignment, clarity, and readiness for applied learning. | Desk review; readiness interview; scoring for alignment, urgency, and capacity to implement. | Finalists gather draft strategy, theory of change, logic model, or community action plan. | Final cohort selections. |
| Thursday, June 18 2 hours, Virtual | Pre-Launch Office Hours | Close readiness gaps before formal launch and orient teams to expectations. | Walk-through of timeline, team roles, technology, and expectations; open Q&A; introduction to baseline tools. | Complete readiness intake before the session. | Readiness issues logged and resolved. |
| Tuesday, June 23 2 hours, Virtual | Baseline Diagnostic + Case Framing | Establish a baseline for skill growth and anchor each team in one concrete initiative. | Diagnostic review; live-case framing exercise; mini-lesson on project management as community infrastructure; peer introductions. | Teams complete baseline diagnostic and draft a one-paragraph case statement. | Readiness intake; baseline skill profile; draft Initiative Profile v1. |

Phase 1 ¦ July 2026 – Grounding the Work What does culturally responsive project management require when the work is community-rooted, collaborative, and intended to shape multi-generational futures?

| Date / Time | Session | Learning Objectives | Agenda / Methods | Pre-work | Output(s) |
| --- | --- | --- | --- | --- | --- |
| Tuesday, July 7 1:00–3:00 PM ET | Session 1 Cohort Launch | Build trust, frame rooted/pwr, and introduce the fellowship as a culturally responsive project management practice lab. | Welcome; values and cohort agreements; appreciative inquiry framing; initiative introductions; mini-lesson on project management, legitimacy, and catalytic capital; reflection. | Read welcome packet and bring one example of an initiative that stalled because execution systems were weak. | Initiative Profile v1; cohort agreements. |
| Thursday, July 16 1:00–3:00 PM ET | Session 2 Power, Roles, and Shared Ownership | Clarify the distinct role of the community steward representative, project lead, and resident/community stakeholder without flattening power or accountability. | Role-mapping; authority and accountability exercise; team operating agreements; case-based discussion on extractive participation versus real shared leadership. | Complete role reflection and identify current decision bottlenecks in the live case. | Role + Decision Map; draft team operating agreement. |
| Tuesday, July 28 1:00–3:00 PM ET | Session 3 Strategy Clarity and Catalytic Capital | Connect the live initiative to broader strategic intent, catalytic capital readiness, and measurable value creation. | Mini-teach on catalytic capital and readiness signals; Strategic Doing lens; strategy-to-initiative mapping; peer consultancy on each case. | Revise the Initiative Profile using comments from Sessions 1 and 2. | Strategy Clarity Brief; problem, possibility, and proof-point statement. |
| Thursday, July 30 1:00–2:30 PM ET | Applied Lab 1 | Pressure-test each team’s case, sharpen goals for August, and identify coaching needs. | Small-group coaching; faculty feedback; live-case diagnostic; August success planning. | Submit Strategy Clarity Brief 48 hours in advance. | Diagnostic Debrief Memo; August growth edge. |

Phase 2 ¦ August–Early September 2026 – Building the Core Muscle What disciplined practices help community-rooted projects move from good intentions to coordinated action without losing people, purpose, or power?

| Date / Time | Session | Learning Objectives | Agenda / Methods | Pre-work | Output(s) |
| --- | --- | --- | --- | --- | --- |
| Thursday, August 6 1:00–3:00 PM ET | Session 4 Scope, Outcomes, and Accountability | Translate ambition into scoped work, near-term outcomes, and better-off measures that match the reality of community-rooted implementation. | Scope statement workshop; output-outcome distinction; better-off measure introduction; peer review; examples from community initiatives. | Bring current plans, logic models, or project notes tied to the live case. | Scope + Outcomes Sheet. |
| Tuesday, August 18 1:00–3:00 PM ET | Session 5 Sequencing, Dependencies, and Work Planning | Build a usable 90-day implementation work plan with clear milestones, dependencies, owners, and timing. | Workback planning; dependency mapping; milestone setting; critical path discussion; team drafting time. | List all known tasks, deadlines, approvals, and recurring meetings tied to the live case. | 90-Day Work Plan; Dependency Map. |
| Thursday, August 27 1:00–3:00 PM ET | Session 6 Collaborative Tables and Stakeholder Alignment | Strengthen the team’s ability to convene, manage, and move collaborative work across multiple stakeholders and power positions. | Collaborative table anatomy; facilitation scenarios; stakeholder mapping; communication cadence design; standard share-out format. | Map current stakeholders, standing meetings, and decision points linked to the initiative. | Collaborative Table Design Memo; Stakeholder Map; standard Share-Out Template. |
| Thursday, September 3 1:00–2:30 PM ET | Applied Lab 2 | Prepare teams for the Baltimore convening by identifying real tensions, stalled decisions, and scenarios they want to test in person. | Faculty consults; scenario harvesting; review of draft work plans; peer feedback. | Submit draft work plan and collaborative table memo in advance. | Convening prep brief; scenario list for Baltimore. |

Phase 3 ¦ September 2026 – Baltimore Convening How do rooted teams practice implementation in real time, under real conditions, while deepening strategy, alignment, and public legitimacy?

| Date / Time | Session | Learning Objectives | Agenda / Methods | Pre-work | Output(s) |
| --- | --- | --- | --- | --- | --- |
| Tuesday, September 15 Baltimore – PM | Convening Day 1 Grounding in Place | Build trust, situate project management in place-based practice, and connect implementation to public leadership and community legitimacy. | Arrival; place-based grounding; opening dinner; framing conversation on Baltimore as a site of economic revitalization, public-private coordination, and community learning. | Teams arrive with convening prep brief and one live implementation tension they want help solving. | Shared cohort commitments for the convening; refined case challenge. |
| Wednesday, September 16 Baltimore – Full Day | Convening Day 2 Intensive Practice | Stress-test work plans, decision rights, and facilitation choices under real implementation conditions. | Morning design lab; public leadership dialogue; afternoon scenario practice on conflict, stakeholder drift, funding uncertainty, and community mistrust; peer consultancies. | Review team materials and assign facilitation roles before travel. | Risk + Scenario Plan; revised Role + Decision Map; revised 90-Day Work Plan. |
| Thursday, September 17 Baltimore – Half Day | Convening Day 3 Forward Planning | Translate in-person learning into a realistic fall execution approach with shared accountability. | Team work time; fall commitments; capstone preview; closing reflection. | Capture notes from Day 2 scenario practice and identify unresolved questions. | Fall Action Commitments; capstone outline; coaching requests. |

Phase 4 ¦ October–November 2026 – Applied Practice and Proof Points What does it take to sustain disciplined execution, adapt in public, and generate proof points that build credibility for future investment?

| Date / Time | Session | Learning Objectives | Agenda / Methods | Pre-work | Output(s) |
| --- | --- | --- | --- | --- | --- |
| Tuesday, October 6 1:00–3:00 PM ET | Session 7 Risk, Adaptation, and Escalation | Normalize disciplined course correction and help teams distinguish between strategic pivots and avoidable drift. | Risk register practice; escalation paths; adaptation scenarios; group troubleshooting. | Bring at least one risk that emerged after Baltimore and one example of a task that shifted. | Risk Register; Pivot Protocol. |
| Thursday, October 22 1:00–3:00 PM ET | Session 8 Measurement, Monitoring, and Meaning-Making | Create light but credible monitoring practices that combine qualitative and quantitative evidence. | Mini-teach on progress monitoring; better-off measures revisited; documentation templates; team work time with sample data. | Bring current notes, outputs, and any data produced since September. | Progress Monitoring Tracker; draft Proof Points Log. |
| Tuesday, November 5 1:00–3:00 PM ET | Session 9 Sustainability and Internalization | Identify which routines, tools, and governance practices should remain after the fellowship ends. | Internalization mapping; standard operating practice discussion; role transfer and documentation planning; peer examples. | Complete a short reflection on which rooted/pwr tools the team is already using and what is still fragile. | Sustainability + Internalization Plan. |
| Thursday, November 19 1:00–3:00 PM ET | Session 10 Capstone Reflection and Proof Points | Close the formal fellowship by surfacing what changed in confidence, systems, execution, and shared leadership. | Final team presentations; before-and-after reflection; proof point gallery walk; celebration; next-step commitments. | Finalize capstone materials and submit updated proof points log in advance. | Capstone Deck; Proof Points Memo; final reflection survey. |
| Thursday, December 10 Optional – 90 min | Post-Program Follow-Up | Encourage immediate carry-forward and document early continuation of practice after the fellowship closes. | Optional ninety-minute close-out office hour for light-touch follow-up and documentation. | Teams share one implementation update and one remaining barrier. | Close-out notes; early continuation snapshot. |

# Cross-Cutting Design Commitments

| Design Commitment | How It Shows Up in rooted/pwr |
| --- | --- |
| Culturally Responsive PM Throughout | Culture is not isolated into one session. Power-sharing, resident legitimacy, facilitation practice, communication, evidence interpretation, and sustainability are threaded throughout the entire sequence. |
| Live-Case Learning | Every team brings one active initiative that serves as the anchor for exercises, labs, assignments, peer feedback, and capstone reflection. |
| Tuesday and Thursday Cadence | The sequence uses Tuesday and Thursday meetings only, with Tuesdays functioning as the primary spine and Thursdays used for labs, deeper practice, office hours, or capstone touchpoints. |
| Team-Based Learning | The three-person team model increases internal transfer, reduces dependency on a single staff person, and makes it more likely that practice changes outlast the fellowship. |
| Proof Points Over Polish | The fellowship closes with evidence of changed practice, not only participant satisfaction. Teams are expected to leave with artifacts they can keep using. |

# Resource and Template Bundle

All resources are released in alignment with the phase in which they are first needed. Teams will receive digital access through the fellowship Google Site.

| Resource / Tool | Purpose | Release Timing |
| --- | --- | --- |
| Readiness Intake | Captures live case, current implementation barriers, team composition, and desired proof points. | Application close to June onboarding |
| Baseline Diagnostic | Identifies confidence and skill levels across planning, facilitation, stakeholder management, sequencing, and measurement. | Before June 23 |
| Initiative Profile Template | One-page snapshot of the live case that can evolve across the fellowship. | June |
| Role + Decision Map | Clarifies authority, shared leadership, and escalation pathways across the three-person team. | July |
| Scope + Outcomes Sheet | Links activities, outputs, outcomes, and better-off measures to the live case. | August |
| 90-Day Work Plan Template | Workback schedule with milestones, owners, dependencies, and notes. | August |
| Collaborative Table Memo + Share-Out Template | Supports meeting design, follow-through, and concise reporting across stakeholders. | August |
| Risk Register + Pivot Protocol | Helps teams document risk, adaptation decisions, and unresolved tensions. | September–October |
| Proof Points Log | Tracks early evidence that rooted project management is shifting practice, coordination, and credibility. | October |
| Capstone Deck Template | Provides a common format for final reflection, artifacts, and next-step commitments. | November |